## Timeline
Project Name |  | Total Duration(Days) | Start Date | End Date | Submission date
Online FIR System |  | 35 | 2021-08-20 | 2021-09-25 | 2021-09-27
Sl No. | Task Descriptions | Start Date | End Date | Duration
1 | Planning/Design
1.1 | Project Defination | 2021-08-20 | 2021-08-21 | 1 Days
1.2 | Finish webpage | 2021-08-22 | 2021-09-10 | 20 Days
1.3 | Project Design | 2021-08-22 | 2021-09-10 | 20 Days
2 | Coding
2.1 | Phase 1 | 2021-08-22 | 2021-09-10 | 20 Days
2.2 | Phase 2 | 2021-09-11 | 2021-09-25 | 15 Days
2.3 | Additional Features | 2021-09-11 | 2021-09-25 | 15 Days
3 | Testing
3.1 | Phase 1 Testing | 2021-09-10 | 2021-09-15 | 6 Days
3.2 | Modification /Any changes | 2021-09-10 | 2021-09-15 | 6 Days
3.3 | Phase 2 Testing | 2021-09-20 | 2021-09-25 | 6 Days
3.4 | Modification /Any changes | 2021-09-20 | 2021-09-25 | 6 Days
3.5 | Final Testing | 2021-09-20 | 2021-09-25 | 6 Days
4 | Documentation
4.1 | User Guide | 2021-09-20 | 2021-09-25 | 6 Dyas
4.2 | Presentation | 2021-09-21 | 2021-09-25 | 6 Dyas

## Roles & Responsiblity
Roles And Responsibilities
1 | Role | Backend Development
| Member Name | Rohit Balasaheb Ankalkhope
| PRN No | 210543181080
| Description | BackEnd Code and Operations and Database
2 | Role | Backend Development
| Member Name | Pavankumar Balaso Patil
| PRN No | 210543181062
| Description | BackEnd Code and Operations and Database
3 | Role | FrontEnd Development
| Member Name | Rohan Rajendra Pawar
| PRN No | 210543181068
| Description | FrontEnd Code and Operations
4 | Role | FrontEnd Development
| Member Name | Tushar Sanjay Shinde
| PRN No | 210543181099
| Description | FrontEnd Code and Operations